rConfig Project Plan

1. Project Overview

The objective of the rConfig project is to implement a network device configuration management solution for the SNA infrastructure, streamlining device configurations and ensuring efficient management. This initiative will involve identifying and engaging key stakeholders across various departments, gathering requirements, designing and customizing the rConfig system, and eventually rolling it out in a controlled manner. Regular monitoring, support, and optimization will follow to ensure the system meets all operational needs.

- Project Sponsor: [Lenny]

- Project Manager: [Stacy]

- Network Engineers: [ Chase, Grey ]

- Principle Engineer [Peter]

2. Project Milestones

- M1: Project Initiation

- Task 1: Objective Definition- peter- completed- for peters part - sna needs to reinstall a server and we need to reintegrate to Zabbix- pending

-Define the goal of implementing rConfig for network device configuration management.

- Task 2: Stakeholder Identification- completed
-Identify key stakeholders, including Operations Manager, Account Manager- mommy alexis, Customer Success, Program Managers, IT Net, and IT Dev. (no need for it dev and it net)

- M2: Planning

- Task 1: Requirements Gathering- peter, lenny, alexis – 3 weeks

-Collect specific needs such as types of network devices to be managed, configuration backup frequency, and automation requirements.

- Task 2: Resource Allocation- this is after project handover

Assign roles, including a project manager, network engineers, and system administrators.

- Task 3 : Timeline and Milestones- peter-5 weeks

-Establish key milestones, including installation, configuration, testing, and go-live, with clear deadlines.

- Task 4: Risk Management- peter- all software servers is on sna own network so its low risk, integration from our rconfig to Zabbix is low out from its read only. – its part of risk management (ongoing)

-Identify potential risks like integration issues or security concerns and plan mitigation strategies.

- M3: Design

- Task 1: System Architecture  - peter- completed

Design the rConfig setup, considering server specifications, network architecture, and integration points with existing systems.

- Task 2: Interface Design- peter- completed

Plan the user interface layout for ease of use by network engineers.

- Task 3: Documentation- peter, alexis- 4-6 weeks

Prepare detailed documentation outlining the rConfig architecture, workflows, and user roles.

- M4: Development

- Task 1: System Configuration- peter- pending reinstalment of server

-Install rConfig on the designated server, configure dependencies, and set up the initial environment.

- Task 2: Customization- peter completed

-Tailor rConfig with necessary plugins, scripts, and templates specific to the network devices in use.

- Task 3: Testing- peter- completed in dev lab

Conduct unit testing, integration testing, and user acceptance testing (UAT) to ensure rConfig meets all specified requirements.

- M5: Implementation

- Task 1: Deployment- peter- 4 weeks

-Roll out rConfig gradually, starting with a pilot group of network devices before a full-scale deployment.

- Task 2: Data Migration- peter- 4 weeks

-Migrate existing network device configurations to rConfig for centralized management.

-Task 3: Training- peter- 5 weeks

Provide training sessions for network engineers and administrators to ensure they are proficient in using rConfig.

- Task 4: Go-Live- peter- 6-8 weeks

-Transition to using rConfig for managing network device configurations, with close monitoring for any issues.

- M6: Post-Implementation

-Task 1: Monitoring and Support- out of scope- we do not monitor the server

Continuously monitor rConfig’s performance and offer ongoing support to address any emerging issues.

- Task 2: Evaluation- user feedback will be after agents go live on the system

Gather user feedback to assess the effectiveness of rConfig and identify areas for improvement.

- Task 3: Optimization- will depend after agents go live

Implement necessary optimizations based on feedback and system performance data to enhance efficiency.

- M7: Project Closure

-Task 1: Final Review- peter, stacy - 8- weeks

-Conduct a comprehensive review of the rConfig implementation, documenting successes and lessons learned.

-Task 2: Handover- peter- 8-10 weeks

-Transition rConfig ownership to the operational team, ensuring all documentation and training materials are up-to-date.

-Task 3:Sign-Off-peter-10 weeks

Obtain final approval from stakeholders and formally close the rConfig project.

3. Project Milestones

- M1: Project Initiation

- M2: Planning

- M3: Design

- M4: Development

- M5: Implementation

- M6: Post-Implementation

- M7: Project Closure