Project Overview

This project aims to transition SNA's communication systems to Zoom for improved global presence, advanced IVR tools, and AI-driven features. The integration with quality assurance systems will enhance customer experience monitoring and response. The goal is to ensure a seamless transition without affecting service quality.

Project Owners:

- Project Sponsor: Shelley Tabernero

- Project Manager: Rain Asia

Project Phases and Milestones

M1: Planning and System Assessment (2 Weeks)

Task 1.1: Kickoff Meeting

- Define the project scope, deliverables, and timeline.

- Identify stakeholders, including technical, operational, and quality assurance teams.

Task 1.2: System and IVR Assessment

- Review current IVR systems, Odyssey CX integration, and communication channels.

- Identify potential risks and develop rollback procedures.

Task 1.3: Resource Allocation and Risk Planning

- Assign roles for migration, testing, and reporting.

- Identify high-risk areas, including system outages, and plan mitigation strategies (e.g., outage announcement systems).

M2: Migration and Testing (Weeks 1-3)

Task 2.1: IVR Migration and Integration

- Migrate all IVR systems to Zoom.

- Perform testing to ensure IVRs are correctly mapped and functional.

Task 2.2: Outage Announcement Systems Setup

- Establish systems to inform users of outages or disruptions in services.

Task 2.3: Quality Assurance Integration Testing

- Test integration with Odyssey CX, ensuring that call transcriptions, customer scoring, and ticketing integration function correctly.

Task 2.4: Reporting and Validation

- Validate reporting capabilities, ensuring that roll call records and reports meet hospitality brand requirements.

- Ensure reporting integrates seamlessly with Odyssey CX.

Task 2.5: Rollback Setup

- Establish rollback procedures for use if the migration encounters critical issues.

M3: Final Testing and Cutover (Weeks 4-5)

Task 3.1: Final System Testing

- Conduct comprehensive testing to ensure system stability and performance.

- Validate IVR functionality, call quality, and reporting accuracy.

Task 3.2: Final Cutover

- Perform the cutover to Zoom on the scheduled date (August 22nd).

- Monitor the system for any immediate post-cutover issues.

M4: Post-Implementation Monitoring and Optimization (1 Month)

Task 4.1: Continuous Monitoring

- Monitor the performance of Zoom integration, focusing on audio quality, IVR functionality, and ticketing integration.

- Track real-time feedback through Odyssey CX to ensure customer satisfaction.

Task 4.2: User Feedback and System Optimization

- Gather feedback from end-users and stakeholders to identify any issues or areas for improvement.

- Optimize IVR flows, reporting, and system integrations based on feedback.

Task 4.3: Support and Maintenance

- Implement short-term post-deployment support to address any emerging issues with Zoom or Odyssey CX.

Project Milestones

- M1: Planning and System Assessment

- M2: Migration and Testing

- M3: Final Testing and Cutover

- M4: Post-Implementation Monitoring and Optimization