## Sheet2
Milestone | Task | Start Date | End Date | Owner | Status | Priority | Dependencies | Comments/Feedback
M1: Planning and Setup | 1.1 Kickoff Meeting - Define scope, deliverables, and assign roles |  |  |  | Not Started | High | -
| 1.2 System Review - Assess current Sangoma PBX and Teams setup |  |  |  | Not Started | High | -
| 1.3 Resource Allocation - Allocate SBCs, SIP trunks, hardware |  |  |  | Not Started | Medium | Kickoff meeting
M2: Configuration and Integration | 2.1 SBC Setup - Install and configure Sangoma SBCs |  |  |  | Not Started | High | Equipment confirmation
| 2.2 Routing and Dial Plan Configuration - Set up voice routes |  |  |  | Not Started | High | SBC setup
| 2.3 User Management - Configure profiles and permissions |  |  |  | Not Started | Medium | Routing rules setup
M3: Security and Compliance | 3.1 Security Measures - Implement security protocols |  |  |  | Not Started | High | Assign phone numbers
| 3.2 Compliance Validation - Conduct audits for compliance |  |  |  | Not Started | High | Centralize user profiles
M4: Testing and Validation | 4.1 Functional Testing - Test calls, call transfers, routing |  |  |  | Not Started | High | Configuration completed
| 4.2 Load Testing - Ensure system stability under high volume |  |  |  | Not Started | High | Functional testing
| 4.2 User Acceptance Testing (UAT) - Validate features with users |  |  |  | Not Started | Medium | Load testing
M5: Deployment | 5.1 Pilot Deployment - Small group deployment, gather feedback |  |  |  | Not Started | Medium | User acceptance testing
| 5.2 Full-Scale Deployment - Roll out to all users, monitor issues |  |  |  | Not Started | High | Pilot deployment
M6: Post-Implementation Support | 6.1 Monitoring and Support - Monitor performance and updates |  |  |  | Not Started | Medium | Full-scale deployment
| 6.2 Feedback Collection - Optimize system based on feedback |  |  |  | Not Started | Low | Post-launch monitoring