Project Plan: PBXact Integration with Microsoft Teams Using Sangoma FreeSBC

Project team :

Main architect - Rain Asia

Purchasing: Danny Wu

Product Support: Kyle Finnelson

Customer Success: Meagan

Week 1: Planning and Preparation

1. Define Project Scope and Objectives

- Understand the need for PBXact and Microsoft Teams integration and pricing

- Identify the team members involved, including network administrators and engineers.

- Confirm required hardware, licenses, and software installations.

2. Verify Infrastructure Requirements

- Confirm PBXact system is fully operational and updated.

- Ensure that the appropriate Microsoft 365 licenses (E5, or E3 with Phone System add-on) are in place.

- Obtain a valid public IP address for FreeSBC and PBXact (if necessary).

- Procure TLS certificates from a trusted Certificate Authority for FreeSBC.

3. Install and Configure Sangoma FreeSBC

- Download and install FreeSBC on a suitable server or virtual machine.

- Verify system requirements and set up initial configuration, including network settings and access to the FreeSBC web interface.

4. Kickoff Meeting

- Hold a project kickoff meeting to discuss timeline, deliverables, and roles.

Week 2: FreeSBC and PBXact Configuration

1. Configure SIP Trunks Between PBXact and FreeSBC

- Set up a SIP trunk in PBXact pointing to FreeSBC.

- In FreeSBC, create a SIP profile for PBXact, ensuring proper authentication and connection.

2. Create Initial Call Routing Rules

- Configure outbound call routing rules on PBXact to route Teams-related calls to FreeSBC.

- Configure FreeSBC’s inbound and outbound routing to handle SIP signaling between PBXact and Teams.

3. Install TLS Certificates

- Install valid TLS certificates on FreeSBC for Microsoft Teams to enable secure communications.

- Ensure the certificate common name (CN) matches the FQDN for FreeSBC.

4. Verify Firewall Configuration

- Ensure that firewalls allow the required ports for SIP, RTP, and TLS traffic (ports like 5061 for SIP-TLS and RTP range).

- Verify PBXact and FreeSBC are accessible over the internet, considering public IPs and NAT if necessary.

Week 3: Microsoft Teams Configuration and Integration

1. Enable Direct Routing in Microsoft Teams

- Log in to the Microsoft Teams Admin Center.

- Configure Direct Routing and add FreeSBC as an approved SBC using its FQDN.

2. Configure Voice Routing Policies

- Create voice routing policies in Teams to define how calls should be routed to FreeSBC.

- Set up dial plans for Teams users that align with PBXact extensions.

3. Assign Phone Numbers and Licenses

- Assign phone numbers to Teams users and ensure they have the appropriate Phone System licenses.

- Ensure user numbers follow E.164 format and are correctly routed through FreeSBC.

4. Test Internal Call Flow

- Perform initial tests to verify call routing between Teams users and PBXact extensions.

- Troubleshoot any issues related to SIP connectivity, number formatting, or routing errors.

Week 4: Final Testing, Optimization, and Handoff

1. Conduct Full System Testing

- Test all critical call flows:

- Teams to PBXact extensions.

- PBXact to Teams users.

- Outbound PSTN calls from Teams (if applicable).

- Verify features such as voicemail, call transfers, and call forwarding are functioning as expected.

2. Monitor Call Quality and Performance

- Use FreeSBC’s diagnostics tools and monitoring software to check call quality and SIP signaling.

- Ensure optimal media and codec settings between PBXact and Teams for smooth call experiences.

3. Troubleshoot and Resolve Issues

- Address any remaining issues with SIP normalization, call routing, or performance.

- Review firewall configurations, TLS certificates, and SBC setup to ensure security and compliance with Microsoft Teams Direct Routing requirements.

4. Handoff and Documentation

- Document the final system setup, including SIP trunks, routing rules, and Microsoft Teams configurations.

- Conduct training for the team on managing the integrated system.

- Schedule a handoff meeting to review the project’s completion and provide any necessary support documentation.

Deliverables

- Configured FreeSBC and PBXact SIP trunks and routing rules.

- Microsoft Teams Direct Routing setup with working voice routing policies.

- TLS certificates installed and functional.

- Full call flow testing completed with documented results.

- Handoff meeting and training completed.

By the end of Week 4, the PBXact and Microsoft Teams integration via Sangoma FreeSBC will be fully operational, with routing tested and verified.