## Detailed_PBXact_Integration_Pro
Week | Task | Details | Project Owner | Start Date | Finish Date | Status | Side Notes
Week 1 | Define Project Scope and Objectives | Understand integration needs, pricing, team roles, hardware, licenses.
| Verify Infrastructure Requirements | Confirm PBXact operational, Microsoft licenses, IP address, TLS certs. | Danny/Henry | 14th oct |  | In Progress | on Microsoft licenses 10/15- sir danny has asked sir henry to reach out to microsoft to Please check with Microsoft support on the cost for Microsoft Phone System Licensing cost ( since ISL has O365 Business Premium), and the contract term ( monthly vs annual)
| Install and Configure Sangoma FreeSBC | Install FreeSBC, verify requirements, and set up initial configuration.
| Kickoff Meeting | Discuss timeline, deliverables, and roles in kickoff meeting.
Week 2 | Configure SIP Trunks Between PBXact and FreeSBC | Configure SIP trunk in PBXact and SIP profile in FreeSBC.
| Create Initial Call Routing Rules | Set up outbound call routing on PBXact and FreeSBC.
| Install TLS Certificates | Install valid TLS certificates on FreeSBC.
| Verify Firewall Configuration | Ensure firewalls allow SIP, RTP, and TLS traffic.
Week 3 | Enable Direct Routing in Microsoft Teams | Log in to Teams Admin, configure Direct Routing with FreeSBC.
| Configure Voice Routing Policies | Create Teams voice routing policies and dial plans aligned with PBXact.
| Assign Phone Numbers and Licenses | Assign phone numbers and licenses to Teams users.
| Test Internal Call Flow | Perform initial tests to verify call routing between Teams and PBXact.
Week 4 | Conduct Full System Testing | Test critical call flows like Teams to PBXact and vice versa.
| Monitor Call Quality and Performance | Monitor call quality and optimize media and codec settings.
| Troubleshoot and Resolve Issues | Troubleshoot SIP, routing, firewall, or certificate issues.
| Handoff and Documentation | Document system setup and conduct team training, finalize handoff.